## Sheet1
Task | Start Date | Days to complete | KW
REST API for filtered data access | 2019-10-21 | 5 | 43
discrete heat map | 2019-10-28 | 5 | 44
stacked bar chart | 2019-11-04 | 3 | 45
color selection | 2019-11-11 | 2 | 46
performance optimization | 2019-11-14 | 2 | 46
informal user study | 2019-11-14 | 5 | 46
user study feedback implementation | 2019-11-18 | 3 | 46
optional selection of multiple regions | 2019-11-19 | 4 | 47
optionl alert against user bias | 2019-11-25 | 3 | 48
final report | 2019-11-25 | 5 | 48